## Calendar
Calendar
Academic Hours | [7 empty] | Industry Hours | [7 empty] | Color code
Week Starting | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Week No
2023-07-24 | 3 | 0 | 1 | 3 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | Danger zone - final two weeks.
2023-07-31 | 2 | 3 | 3 | 4 | 1 | 3 | 3 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 2
2023-08-07 | 2 | 0 | 0 | 4 | 1 | 0 | 3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 3
2023-08-14 | 4 | 0 | 0 | 4 | 1 | 2 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4
2023-08-21 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 7 | 4 | 0 | 2 | 2 | 5
2023-08-28 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 6
2023-09-04 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 8.5 | 0 | 8.5 | 8 | 4 | 0 | 1 | 7
2023-09-11 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3.5 | 8 | 8 | 8 | 0 | 0 | 0 | 8
2023-09-18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 8 | 8 | 0 | 0 | 0 | 9
2023-09-25 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 10
2023-10-02 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 11 |  |  | sumbit everything!!!!
2023-10-09 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 4.5 | 8 | 8 | 8 | 0 | 0 | 0 | 10
2023-10-16 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11
2023-10-23 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12
2023-10-30 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 4.5 | 8 | 8 | 8 | 0 | 0 | 0 | 13
2023-11-06 | 0 | 0 | 4 | 2 | 0 | 2 | 3 | 4.5 | 8 | 0 | 0 | 8 | 0 | 0 | 14
2023-11-13 | 1 | [6 empty] | 8 | 8 | 8 | 8 |  |  |  | 15
2023-11-20 | [14 empty] | 16
2023-11-27 | [14 empty] | 17

## Burndown
Burndown Charts
Academic
Sasha Stepanov |  | Hours per week |  | Remaining hours
Week No | Week Starting | Planned | Actual | Planned Hours | Actual Hours
1 | 2023-07-24 | 12 | 14 | 150 | 150 | Special designations
2 | 2023-07-31 | 12 | 19 | 138 | 136
3 | 2023-08-07 | 12 | 10 | 126 | 117 |  | Final two weeks.
4 | 2023-08-14 | 12 | 15 | 114 | 107
5 | 2023-08-21 | 3 | 3 | 102 | 92
6 | 2023-08-28 | 3 | 3 | 99 | 89
7 | 2023-09-04 | 3 | 3 | 96 | 86
8 | 2023-09-11 | 3 | 3 | 93 | 83
9 | 2023-09-18 | 3 | 3 | 90 | 80
10 | 2023-09-25 | 6 | 6 | 87 | 77
11 | 2023-10-02 | 6 | 3 | 81 | 71
12 | 2023-10-09 | 15 | 6 | 75 | 68
13 | 2023-10-16 | 5 | 4 | 60 | 62
14 | 2023-10-23 | 5 | 4 | 55 | 58
15 | 2023-10-30 | 5 | 5 | 50 | 54
16 | 2023-11-06 | 5 | 11 | 45 | 49
17 | 2023-11-13 | 20 | 1 | 40 | 38
18 | 2023-11-20 | 20 | 0 | 20 | 37
19 | 2023-11-27 | 0 | 0 | 0 | 37
| Total | 150 | 113
Industry
Sasha Stepanov |  | Hours per week |  | Remaining hours
Week No | Week Starting | Planned | Actual | Planned Hours | Actual Hours
1 | 2023-07-24 | 0 | 0 | 300 | 300
2 | 2023-07-31 | 0 | 6 | 300 | 300
3 | 2023-08-07 | 5 | 5 | 300 | 294
4 | 2023-08-14 | 5 | 3 | 295 | 289
5 | 2023-08-21 | 22 | 18 | 290 | 286
6 | 2023-08-28 | 22 | 16 | 268 | 268
7 | 2023-09-04 | 22 | 30 | 246 | 252
8 | 2023-09-11 | 22 | 27.5 | 224 | 222
9 | 2023-09-18 | 23 | 24.5 | 202 | 194.5
10 | 2023-09-25 | 23 | 32 | 179 | 170
11 | 2023-10-02 | 23 | 32 | 156 | 138
12 | 2023-10-09 | 23 | 28.5 | 133 | 106
13 | 2023-10-16 | 3 | 3 | 110 | 77.5
14 | 2023-10-23 | 3 | 2 | 107 | 74.5
15 | 2023-10-30 | 35 | 28.5 | 104 | 72.5
16 | 2023-11-06 | 35 | 20.5 | 69 | 44
17 | 2023-11-13 | 34 | 32 | 34 | 23.5
18 | 2023-11-20 | 0 | 0 | 0 | -8.5
19 | 2023-11-27 | 0 | 0 | 0 | -8.5
| Total | 300 | 308.5

## Change of Circumstances
An explanation of the difference between planned and actual time expenditure will be presented here.Note : Only significant situations with a time difference of at least 2 hours will be considered.
ID | time situation | Reason | what does it mean | required action
ac-week2 | Went over the limit. | Acquaintance with the project took place earlier and faster than planned, there was no point in postponing the writing of the proposal for later. "Strike while the iron is hot". | Probably will leave an impact on a whole academic deliverables, will take longer to finish. | Time should be spent on academic deliverables more wisely and carefully.
ind-week2 | Went over the limit. | The project was found in a short time, it became possible to get to know the project, the company and the team earlier. | It means,maybe,early finish. | None
ind-week5 | missed one day of work. | Personal reason. | Will have to catch up as soon as possible. | Will have to work an extra hours in the next few weeks to be able to get back on track
ind-week6 | missed one day of work. | Unavailability of industrial supervisor. | Will have to catch up as soon as possible. | Will have to work an extra hours in the next few weeks to be able to get back on track
ind-week7 | Worked an extra hours. | To catch up on schedule. | Project is on track (hours wise). | None
ind-week8 | Worked an extra hours. | To catch up on schedule. | Project is on track (hours wise). | None
ind-week10 | Worked an extra hours. | There was an opportunity to work more so the hours increased. | It means,maybe,early finish. | None
ind-week11 | Worked an extra hours. | There was an opportunity to work more so the hours increased. | It means,maybe,early finish. | None
ac-week11 | Less than planned time was spent writing the halfway report. | Ovestimated Complexity of Halfway Report. | The likelihood of catching up on the clock increases. | Continue in the same spirit to make up for the hours spent writing the project proposal.
ac-week12 | Less than planned time was spent writing the halfway report. | Ovestimated Complexity of Halfway Report. | The likelihood of catching up on the clock increases. | Continue in the same spirit to make up for the hours spent writing the project proposal.
ind-week12 | Worked an extra hours. | There was an opportunity to work more so the hours increased. | It means,maybe,early finish. | None
At this stage, the original work plan of the industry was changed, namely the number of hours. As described in the report, this is due to the absence of the supervisor for two weeks, and therefore it was necessary to adjust the planned hours in order to have time to work everything within the given time frame.
ind-week15 | Fewer hours were worked than planned. | This is due to the fact that the student worked overtime earlier, so the student may work less than planned hours. | There are no significant changes for the project. | Monitor hours worked and planned dates to complete the project within the allotted time frame.
ac-week16 | Went over the limit.
ind-week16 | Fewer hours were worked than planned.