## Calendar
Calendar
Academic Hours | [7 empty] | Industry Hours | [7 empty] | Color code
Week Starting | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Week No
2023-07-24 | 3 | 0 | 1 | 3 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | Danger zone - final two weeks.
2023-07-31 | 2 | 3 | 3 | 4 | 1 | 3 | 3 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 2
2023-08-07 | 2 | 0 | 0 | 4 | 1 | 0 | 3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 3
2023-08-14 | 4 | 0 | 0 | 4 | 1 | 2 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4
2023-08-21 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 7 | 4 | 0 | 2 | 2 | 5
2023-08-28 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 6
2023-09-04 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 8.5 | 0 | 8.5 | 8 | 4 | 0 | 1 | 7
2023-09-11 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3.5 | 8 | 8 | 8 | 0 | 0 | 0 | 8
2023-09-18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 8 | 8 | 0 | 0 | 0 | 9
2023-09-25 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 10
2023-10-02 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 11
2023-10-09 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 4.5 | 8 | 8 | 8 | 0 | 0 | 0 | 10
2023-10-16 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11
2023-10-23 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12
2023-10-30 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 4.5 | 8 | 8 | 8 | 0 | 0 | 0 | 13
2023-11-06 | [14 empty] | 14
2023-11-13 | [14 empty] | 15
2023-11-20 | [14 empty] | 16
2023-11-27 | [14 empty] | 17

## Burndown
Burndown Charts
Academic
Sasha Stepanov |  | Hours per week |  | Remaining hours
Week No | Week Starting | Planned | Actual | Planned Hours | Actual Hours
1 | 2023-07-24 | 12 | 14 | 150 | 150 | Special designations
2 | 2023-07-31 | 12 | 19 | 138 | 136
3 | 2023-08-07 | 12 | 10 | 126 | 117 |  | Final two weeks.
4 | 2023-08-14 | 12 | 15 | 114 | 107
5 | 2023-08-21 | 3 | 3 | 102 | 92
6 | 2023-08-28 | 3 | 3 | 99 | 89
7 | 2023-09-04 | 3 | 3 | 96 | 86
8 | 2023-09-11 | 3 | 3 | 93 | 83
9 | 2023-09-18 | 3 | 3 | 90 | 80
10 | 2023-09-25 | 6 | 6 | 87 | 77
11 | 2023-10-02 | 6 | 3 | 81 | 71
12 | 2023-10-09 | 15 | 6 | 75 | 68
13 | 2023-10-16 | 5 | 4 | 60
14 | 2023-10-23 | 5 | 4 | 55 | 62
15 | 2023-10-30 | 5 | 5 | 50 | 58
16 | 2023-11-06 | 5 | 0 | 45 | 54
17 | 2023-11-13 | 20 | 0 | 40 | 49
18 | 2023-11-20 | 20 | 0 | 20 | 49
19 | 2023-11-27 | 0 | 0 | 0
| Total | 150
Industry
Sasha Stepanov |  | Hours per week |  | Remaining hours
Week No | Week Starting | Planned | Actual | Planned Hours | Actual Hours
1 | 2023-07-24 | 0 | 0 | 300 | 300
2 | 2023-07-31 | 6 | 6 | 300 | 300
3 | 2023-08-07 | 5 | 5 | 294 | 294
4 | 2023-08-14 | 3 | 3 | 289 | 289
5 | 2023-08-21 | 18 | 18 | 286 | 286
6 | 2023-08-28 | 16 | 16 | 268 | 268
7 | 2023-09-04 | 30 | 30 | 252 | 252
8 | 2023-09-11 | 27.5 | 27.5 | 222 | 222
9 | 2023-09-18 | 24.5 | 24.5 | 194.5 | 194.5
10 | 2023-09-25 | 32 | 32 | 170 | 170
11 | 2023-10-02 | 32 | 32 | 138 | 138
12 | 2023-10-09 | 28 | 28.5 | 106 | 106
13 | 2023-10-16 | 3 | 3 | 78 | 77.5
14 | 2023-10-23 | 3 | 2 | 75 | 74.5
15 | 2023-10-30 | 28 | 28.5 | 72 | 72.5
16 | 2023-11-06 | 23 | 0 | 44 | 44
17 | 2023-11-13 | 21 | 0 | 21 | 44
18 | 2023-11-20 | 0 | 0 | 0
19 | 2023-11-27 | 0 | 0 | 0
| Total | 300 | 256

## Change of Circumstances
An explanation of the difference between planned and actual time expenditure will be presented here.Note : Only significant situations with a time difference of at least 2 hours will be considered.
ID | time situation | Reason | what does it mean | required action
ac-week2 | Went over the limit. | Acquaintance with the project took place earlier and faster than planned, there was no point in postponing the writing of the proposal for later. "Strike while the iron is hot". | Probably will leave an impact on a whole academic deliverables, will take longer to finish. | Time should be spent on academic deliverables more wisely and carefully.
ind-week2 | Went over the limit. | The project was found in a short time, it became possible to get to know the project, the company and the team earlier. | It means,maybe,early finish. | None
ind-week5 | missed one day of work. | Personal reason. | Will have to catch up as soon as possible. | Will have to work an extra hours in the next few weeks to be able to get back on track
ind-week6 | missed one day of work. | Unavailability of industrial supervisor. | Will have to catch up as soon as possible. | Will have to work an extra hours in the next few weeks to be able to get back on track
ind-week7 | Worked an extra hours. | To catch up on schedule. | Project is on track (hours wise). | None
ind-week8 | Worked an extra hours. | To catch up on schedule. | Project is on track (hours wise). | None
ind-week10 | Worked an extra hours. | There was an opportunity to work more so the hours increased. | It means,maybe,early finish. | None
ind-week11 | Worked an extra hours. | There was an opportunity to work more so the hours increased. | It means,maybe,early finish. | None
ac-week11 | Less than planned time was spent writing the halfway report. | Ovestimated Complexity of Halfway Report. | The likelihood of catching up on the clock increases. | Continue in the same spirit to make up for the hours spent writing the project proposal.