## Calendar
Calendar
Academic Hours | [7 empty] | Industry Hours | [7 empty] | Color code
Week Starting | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Week No
2023-07-24 | 3 | 0 | 1 | 3 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | Danger zone - final two weeks.
2023-07-31 | 2 | 4 | 4 | 5 | 0 | 3 | 3.5 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 2
2023-08-07 | 2 | 0 | 0 | 5 | 0 | 0 | 3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 3
2023-08-14 | 5 | 0 | 0 | 4 | 0 |  |  | 0 | 0 | 0 | 3 | 0 |  |  | 4
2023-08-21 | [14 empty] | 5
2023-08-28 | [14 empty] | 6
2023-09-04 | [14 empty] | 7
2023-09-11 | [14 empty] | 8
2023-09-18 | [14 empty] | 9
2023-09-25 | [14 empty] | 10
2023-10-02 | [14 empty] | 11
2023-10-09 | [14 empty] | 10
2023-10-16 | [14 empty] | 11
2023-10-23 | [14 empty] | 12
2023-10-30 | [14 empty] | 13
2023-11-06 | [14 empty] | 14
2023-11-13 | [14 empty] | 15
2023-11-20 | [14 empty] | 16
2023-11-27 | [14 empty] | 17

## Burndown
Burndown Charts
Academic
| Sasha Stepanov |  | Hours per week |  | Remaining hours
| Week No | Week Starting | Planned | Actual | Planned Hours | Actual Hours
| 1 | 2023-07-24 | 12 | 14 | 150 | 150 | Special designations
ID-1 | 2 | 2023-07-31 | 12 | 21.5 | 138 | 136 | BIGGER FONT | change of circumstances
| 3 | 2023-08-07 | 12 | 10 | 126 | 114.5
| 4 | 2023-08-14 | 12 | 9 | 114 | 104.5 |  | Danger zone - final two weeks.
| 5 | 2023-08-21 | 3 | 0 | 102 | 95.5
| 6 | 2023-08-28 | 3 | 0 | 99
| 7 | 2023-09-04 | 3 | 0 | 96
| 8 | 2023-09-11 | 3 | 0 | 93
| 9 | 2023-09-18 | 3 | 0 | 90
| 11 | 2023-09-25 | 6 | 0 | 87
| 12 | 2023-10-02 | 6 | 0 | 81
| 13 | 2023-10-09 | 15 | 0 | 75
| 14 | 2023-10-16 | 5 | 0 | 60
| 15 | 2023-10-23 | 5 | 0 | 55
| 16 | 2023-10-30 | 5 | 0 | 50
| 17 | 2023-11-06 | 5 | 0 | 45
| 18 | 2023-11-13 | 20 | 0 | 40
| 19 | 2023-11-20 | 20 | 0 | 20
| 20 | 2023-11-27 | 0 | 0 | 0
|  | Total | 150
Industry
| Sasha Stepanov |  | Hours per week |  | Remaining hours
| Week No | Week Starting | Planned | Actual | Planned Hours | Actual Hours
| 1 | 2023-07-24 | 0 | 0 | 300 | 300
ID - 2 | 2 | 2023-07-31 | 0 | 6 | 300 | 300
| 3 | 2023-08-07 | 5 | 5 | 300
| 4 | 2023-08-14 | 5 | 3 | 295
| 5 | 2023-08-21 | 22 | 0 | 290
| 6 | 2023-08-28 | 22 | 0 | 268
| 7 | 2023-09-04 | 22 | 0 | 246
| 8 | 2023-09-11 | 22 | 0 | 224
| 9 | 2023-09-18 | 23 | 0 | 202
| 10 | 2023-09-25 | 23 | 0 | 179
| 11 | 2023-10-02 | 23 | 0 | 156
| 12 | 2023-10-09 | 23 | 0 | 133
| 13 | 2023-10-16 | 22 | 0 | 110
| 14 | 2023-10-23 | 22 | 0 | 88
| 15 | 2023-10-30 | 22 | 0 | 66
| 16 | 2023-11-06 | 22 | 0 | 44
| 17 | 2023-11-13 | 22 | 0 | 22
| 18 | 2023-11-20 | 0 | 0 | 0
| 19 | 2023-11-27 | 0 | 0 | 0
|  | Total | 300

## Change of Circumstances
An explanation of the difference between planned and actual time expenditure will be presented here.Note : Only significant situations with a time difference of at least 2 hours will be considered.
ID | Overfulfilled / underfulfilled the plan | Reason
1 | Overfulfilled | Acquaintance with the project took place earlier and faster than planned, there was no point in postponing the writing of the proposal for later. "Strike while the iron is hot".
2 | Overfulfilled | The project was found in a short time, it became possible to get to know the project, the company and the team earlier.
3
4