## Time allocations
| WS3 SAP | WS4 additional | ARA | Total
Edith | 200 |  |  | 200
Rogerio | 40 | 60 |  | 100
Jo | 60 | 140 |  | 200
Sasha |  |  | 300 | 300
Hamish | 129 | 40 |  | 169

## Tasks to complete
Section | Task | Date | Responsible | time | Support1 | Stime1 | Support2 | Stime
Crop coefficients
| Potato cultivar descriptions | 2023-08-30 | Hamish | 20
| Vege coefficients from WS1 and 2 data | 2023-11-30 | WS1&2 |  | Hamish | 2
| Review other sources of data | 2023-11-30 | Hamish | 12 | Jo | 6 | Edith | 6
| Colate data and update coeffs in github | 2023-12-30 | Hamish | 16
| Assemble documentation for coefficients | 2023-12-30 | Hamish | 24 |  | WS1&2
APSIM testing | Data cleaning complete | 2023-11-30 | WS1&2 |  | Edith | 24
| Leaching calculations complete | 2023-12-30 | Rogerio | 30 | Edith | 12
| Update SCRUM model in simulations | 2023-12-30 | Edith | 16 | Hamish | 8
| Model evaluation complete against all WS1 treatments | 2024-02-28 | Edith | 100 | Rogerio | 20 | Jo | 20
| Report on results | 2024-04-30 | Edith | 40
API model testing | WS2 field configurations complete and in version control | 2023-09-15 | Sasha | 40 | Edith |  | Hamish
| Script to run simulations through API complete and in version control | 2023-09-30 | Sasha | 80 | Hamish
| WS2 Observed data formated and in version control | 2023-10-15 | Sasha | 40 | Edith |  | Hamish
| System for visualising model performance complete and in version control | 2023-10-30 | Sasha | 80 | Hamish |  | Jo
| Integrate testing with Git hub pull request process | 2023-11-15 | Sasha | 60 | Hamish
| WS1 field configuration complete and in version control | 2023-11-30 | Hamish | 20 | Edith | 20
| WS1 Observed data formated and in version control | 2023-12-15 | Hamish | 20 | Edith | 20
| Report on model performance | 2024-04-30 | Hamish | 20
Web App Role out | Testing | 2023-12-30 | Hamish | 20
| Bug fixes | 2023-12-30 | Hamish | 20
| Review UI defaults | 2023-12-30 | Hamish | 10 | Bruce | 10
Mineralisation model | Residue mineralisation module formulated with preliminary testing | 2023-09-30 | Jo | 20 | Rogerio | 4
| Data extraction from literature completed | 2023-11-30 | Jo | 40
| Model coefficients fitted for different residue types | 2024-01-30 | Chris | 40 | Jo | 10
| Model integrated into API model and in version control | 2024-02-28 | Jo | 10 | Hamish | 10
| Basic sensibility testing completed | 2024-03-30 | Jo | 30
| Basic model documentation completed | 2024-04-30 | Jo | 30 | Rogerio | 2 | Hamish | 2
Leaching model | Leaching model approach formulated | 2023-10-30 | Hamish | 10 | Rogerio | 4 | Jo | 4
| APSIM simulations completed to provide fitting data | 2023-12-30 | Hamish | 20
| Parameter fitting complete | 2023-02-15 | Hamish | 20 | Rogerio | 5
| Model integrated into API model and in version control | 2023-02-28 | Hamish | 10
| Basic sensibility testing completed | 2023-03-30 | Hamish | 30 | Rogerio | 4 | Jo | 4
| Basic model documentation completed | 2024-04-30 | Hamish | 20 | Rogerio
De/Nitrification model | Modelling approach formulated | 2023-10-30 | Hamish | 10 | Rogerio
| APSIM sensibility conducted | 2023-12-30 | Hamish | 20 | Rogerio | 4 | Jo | 4
| APSIM simulations completed to provide fitting data | 2023-02-15 | Hamish | 20
| Parameter fitting complete | 2023-02-28 | Hamish | 20 | Rogerio | 4
| Model integrated into API model and in version control | 2023-03-30 | Hamish | 10
| Basic model documentation completed | 2024-04-30 | Hamish | 20