## Calendar
Calendar
Academic Hours | [7 empty] | Industry Hours | [7 empty] | Color code
Week Starting | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Week No
2023-07-24 | 3 | 0 | 1 | 3 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | Danger zone - final two weeks.
2023-07-31 | 2 | 3 | 3 | 4 | 1 | 3 | 3 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 2
2023-08-07 | 2 | 0 | 0 | 4 | 1 | 0 | 3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 3
2023-08-14 | 4 | 0 | 0 | 4 | 1 | 2 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4
2023-08-21 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 7 | 4 | 0 | 2 | 2 | 5
2023-08-28 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 6
2023-09-04 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 8.5 | 0 | 8.5 | 8 | 4 | 0 | 1 | 7
2023-09-11 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3.5 | 8 | 8 | 8 | 0 | 0 | 0 | 8
2023-09-18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 8 | 8 | 0 | 0 | 0 | 9
2023-09-25 | [14 empty] | 10
2023-10-02 | [14 empty] | 11
2023-10-09 | [14 empty] | 10
2023-10-16 | [14 empty] | 11
2023-10-23 | [14 empty] | 12
2023-10-30 | [14 empty] | 13
2023-11-06 | [14 empty] | 14
2023-11-13 | [14 empty] | 15
2023-11-20 | [14 empty] | 16
2023-11-27 | [14 empty] | 17

## Burndown
Burndown Charts
Academic
Sasha Stepanov |  | Hours per week |  | Remaining hours
Week No | Week Starting | Planned | Actual | Planned Hours | Actual Hours
1 | 2023-07-24 | 12 | 14 | 150 | 150 | Special designations
2 | 2023-07-31 | 12 | 19 | 138 | 136
3 | 2023-08-07 | 12 | 10 | 126 | 117 |  | Final two weeks.
4 | 2023-08-14 | 12 | 15 | 114 | 107
5 | 2023-08-21 | 3 | 3 | 102 | 92
6 | 2023-08-28 | 3 | 3 | 99 | 89
7 | 2023-09-04 | 3 | 3 | 96 | 86
8 | 2023-09-11 | 3 | 3 | 93 | 83
9 | 2023-09-18 | 3 | 3 | 90 | 80
10 | 2023-09-25 | 6 | 0 | 87
11 | 2023-10-02 | 6 | 0 | 81
12 | 2023-10-09 | 15 | 0 | 75
13 | 2023-10-16 | 5 | 0 | 60
14 | 2023-10-23 | 5 | 0 | 55
15 | 2023-10-30 | 5 | 0 | 50
16 | 2023-11-06 | 5 | 0 | 45
17 | 2023-11-13 | 20 | 0 | 40
18 | 2023-11-20 | 20 | 0 | 20
19 | 2023-11-27 | 0 | 0 | 0
| Total | 150
Industry
Sasha Stepanov |  | Hours per week |  | Remaining hours
Week No | Week Starting | Planned | Actual | Planned Hours | Actual Hours
1 | 2023-07-24 | 0 | 0 | 300 | 300
2 | 2023-07-31 | 0 | 6 | 300 | 300
3 | 2023-08-07 | 5 | 5 | 300 | 294
4 | 2023-08-14 | 5 | 3 | 295 | 289
5 | 2023-08-21 | 22 | 18 | 290 | 286
6 | 2023-08-28 | 22 | 16 | 268 | 268
7 | 2023-09-04 | 22 | 30 | 246 | 252
8 | 2023-09-11 | 22 | 27.5 | 224 | 222
9 | 2023-09-18 | 23 | 24.5 | 202 | 194.5
10 | 2023-09-25 | 23 | 0 | 179 | 170
11 | 2023-10-02 | 23 | 0 | 156
12 | 2023-10-09 | 23 | 0 | 133
13 | 2023-10-16 | 22 | 0 | 110
14 | 2023-10-23 | 22 | 0 | 88
15 | 2023-10-30 | 22 | 0 | 66
16 | 2023-11-06 | 22 | 0 | 44
17 | 2023-11-13 | 22 | 0 | 22
18 | 2023-11-20 | 0 | 0 | 0
19 | 2023-11-27 | 0 | 0 | 0
| Total | 300

## Change of Circumstances
An explanation of the difference between planned and actual time expenditure will be presented here.Note : Only significant situations with a time difference of at least 2 hours will be considered.
ID | time situation | Reason | what does it mean | what to do
ac-week2 | Went over the limit | Acquaintance with the project took place earlier and faster than planned, there was no point in postponing the writing of the proposal for later. "Strike while the iron is hot". | Probably will leave an impact on a whole academic deliverables, will take longer to finish
ind-week2 | Went over the limit | The project was found in a short time, it became possible to get to know the project, the company and the team earlier. | It means,maybe,early finish
ind-week5 | missed one day of work | Personal reason | Will have to catch up as soon as possible.
ind-week6 | missed one day of work | Unavailability of industrial supervisor. | Will have to catch up as soon as possible.
ind-week7 | Worked an extra hours | To catch up on schedule. | Project is on track (hours wise)
ind-week8 | Worked an extra hours | To catch up on schedule. | Project is on track (hours wise)