## Academic Timeline(03.08.2023)
Project NAME
Project Planner: Sasha Stepanov
Review Date: TBA
Delivery Date: TBA
Academic Deliverables
Deliverables | Tasks / Activity | Estimated Time (hrs) | Actual Time (hrs) | Target Date of Completion | Actual Date Completion | Variance (hrs)
W.I.L and Confidentiality Agreement | Signed by people who involved in a project | 1 | 1 |  |  | 0
Project Proposal | Familiarization with a proposal requirements. | 1 | 1 |  |  | 0
| Project Details | 2 | 3 |  |  | -1 | took longer than I planned, it was hard to analyze all gathered data
| Project Scope | 3 | 3 |  |  | 0
| Stakeholder Management | 1 | 1 |  |  | 0
| Student Required Skills | 4 | 4 |  |  | 0
| Project Plan,high-level plan | 8 | 10 |  |  | -2 | Time management took longer, I always had problems with that. Plus I was under the weater…
| Burndown Chart | 4 | 4 |  |  | 0
| Risk Management | 2 | 2 |  |  | 0
| Quality Assurance | 5 | 5 |  |  | 0
| Methodology | 4 | 6 |  |  | -2 | Problem arised as I started to gather more info about company and project itself.
| Professionalism | 4 | 5 |  |  | -1 | Section looked smaller before I started. Simple underestimation.
| Sustainability, Inclusive Practice and Te Tiriti o Waitangi | 4 | 3 |  |  | 1
| Reflections | 3 | 3 |  |  | 0
| Revision of all sections for errors and shortcomings | 3 | TBA |  |  | #VALUE!
Project Proposal Checklist | Checking the proporsal for the presence of all the necessary parts. | 1 | TBA |  |  | #VALUE!
Project Proposal Sign off | Signed by people who involved in a project | 0.5 | TBA |  |  | #VALUE!
Halfway Report | Progress Updates, Reflection, What went well, What did not go well, Improvements | 30 | TBA |  |  | #VALUE!
Methodology Essay | At least 1000 words on the accepted theory or methodology | 7 | TBA |  |  | #VALUE!
| At least 1000 words that describes the industrial practice that was observed while carrying out the project, | 7 | TBA |  |  | #VALUE!
| At least 1000 words that compares and contrasts the theory and observed practice and shows critical reflection. | 6 | TBA |  |  | #VALUE!
Final Report Documentation | Final reflections and Self Evaluation | 20 | TBA |  |  | #VALUE!
| Revision of all chapters of the report and correction of errors. Compliance | 6 | TBA |  |  | #VALUE!
Short Paper | Short Paper summary of your project work based on the CITRENZ template | 5 | TBA |  |  | #VALUE!
Poster | Creation of a poster describing the completed project. | 8 | TBA |  |  | #VALUE!
Panel Presentation | Short Bioography about background and achievement | 2.5 | TBA |  |  | #VALUE!
| Power Point Presentation slides and a speech | 5 | TBA |  |  | #VALUE!
| Practice of speech and presentation | 2 | TBA |  |  | #VALUE!
| Presentation | 1 | TBA |  |  | #VALUE!
0
| Total time | 150 | 51 |  | Total Variance | 99

## Industrial (03.08.2023)
Project NAME
Project Planner: Sasha Stepanov
Review Date: TBA
Delivery Date: TBA
Industrial Deliverables
Deliverables | Tasks / Activity | Estimated Time (hrs) | Actual Time (hrs) | Target Date of Completion | Actual Date Completion | Variance (hrs)
First Phase (Familiarization) | Obtaining and processing all the necessary information in regards that project for proposal. | 4 | 5 |  |  | -1 | At the beginning was little bit frustrated,that is why took longer.
| Signing of all necessary documents such as non-disclosure form, contract and agreements. | 2 | 2 |  |  | 0
| Familiarization with a company,team meeting. | 5 | 5
The second phase creating a prototype model | Search for the necessary information | 5 | 6 |  |  | -1 | It is hard to work with a new tools,languages etc.
| Working on a python model | 50 | TBA |  |  | #VALUE!
| Model testing | 20 | TBA |  |  | #VALUE!
| Documentation | 5 | TBA |  |  | #VALUE!
0
0
The third phase - Model improvement | Working on a python model | 50 | TBA |  |  | #VALUE!
| Model testing | 20 | TBA |  |  | #VALUE!
| Documentation | 5 | TBA |  |  | #VALUE!
0
0
Phase 3.5 as needed. Copy of the third phase. | Working on a python model | TBA | TBA |  |  | #VALUE!
| Model testing | TBA | TBA |  |  | #VALUE!
| Documentation | TBA | TBA |  |  | #VALUE!
4 Phase - Final. Processing of all results and adjustment of model. | TBA | TBA | TBA |  |  | #VALUE!
| TBA | TBA | TBA |  |  | #VALUE!
| TBA | TBA | TBA |  |  | #VALUE!
| TBA | TBA | TBA |  |  | #VALUE!
0
| Total time | 166 | 18 |  | Total Variance | 148