## Academic Timeline(03.08.2023)
Project: SVS Model
Project Planner: Sasha Stepanov
Academic Deliverables
Deliverables | Tasks / Activity | Estimated Time (hrs) | Actual Time (hrs) | Target Date of Completion | Actual Date Completion | Variance (hrs)
W.I.L and Confidentiality Agreement | Signed by people who involved in a project | 1 | 1 | 2023-08-02 | 2023-08-25 | 0
Project Proposal | Familiarization with a proposal requirements. | 1 | 1 | 2023-07-29 | 2023-07-29 | 0
| Project Details | 2 | 3 | 2023-08-02 | 2023-08-05 | -1 | took longer than I planned, it was hard to analyze all gathered data
| Project Scope | 3 | 3 | 2023-08-02 | 2023-08-06 | 0
| Stakeholder Management | 1 | 1 | 2023-08-02 | 2023-08-02 | 0
| Student Required Skills | 4 | 4 | 2023-08-02 | 2023-08-05 | 0 | reviewed after meeting with a supervisor
| Project Plan,high-level plan | 7 | 8 | 2023-08-04 | 2023-08-12 | -1 | reviewed after meeting with a supervisor
| Burndown Chart | 4 | 4 | 2023-07-29 | 2023-07-29 | 0
| Risk Management | 4 | 4 | 2023-08-06 | 2023-08-06 | 0
| Quality Assurance | 5 | 7 | 2023-08-07 | 2023-08-18 | -2 | Did not have anough information about deliverables from industry. reviewed after meeting with a supervisor
| Methodology | 4 | 7 | 2023-08-08 | 2023-08-18 | -3 | Problem arised as I started to gather more info about company and project itself. Plus I had to review after meeting with a supervisor
| Professionalism | 4 | 3 | 2023-07-29 | 2023-07-29 | 1
| Sustainability, Inclusive Practice and Te Tiriti o Waitangi | 4 | 3 | 2023-07-29 | 2023-07-29 | 1
| Reflections | 3 | 3 | 2023-07-29 | 2023-07-29 | 0
| Revision of all sections for errors and shortcomings | 3 | 6 | 2023-08-23 | 2023-08-23 | -3
Project Proposal Checklist | Checking the proporsal for the presence of all the necessary parts. | 1 |  | 2023-08-24 |  | 1
Project Proposal Sign off | Signed by people who involved in a project | 0.5 |  | 2023-08-24 |  | 0.5
Halfway Report | Progress Updates, Reflection, What went well, What did not go well, Improvements | 30 |  | 2023-09-29 |  | 30
Methodology Essay | At least 1000 words on the accepted theory or methodology | 7 |  | 2023-11-27 |  | 7
| At least 1000 words that describes the industrial practice that was observed while carrying out the project, | 7 |  | 2023-11-27 |  | 7
| At least 1000 words that compares and contrasts the theory and observed practice and shows critical reflection. | 6 |  | 2023-11-27 |  | 6
Final Report Documentation | Final reflections and Self Evaluation | 20 |  | 2023-11-27 |  | 20
| Revision of all chapters of the report and correction of errors. Compliance | 6 |  | 2023-11-27 |  | 6
Short Paper | Short Paper summary of your project work based on the CITRENZ template | 5 |  | 2023-11-27 |  | 5
Poster | Creation of a poster describing the completed project. | 8 |  | 2023-11-27 |  | 8
Panel Presentation | Short Bioography about background and achievement | 2.5 |  | 2023-11-27 |  | 2.5
| Power Point Presentation slides and a speech | 4 |  | 2023-11-27 |  | 4
| Practice of speech and presentation | 2 |  | 2023-11-27 |  | 2
| Presentation | 1 |  | 2023-11-27 |  | 1
0
| Total time | 150 | 58 |  | Total Variance | 92

## Industrial (03.08.2023)
Project SVS Model
Project Planner: Sasha Stepanov
Industrial Deliverables
Deliverables | Tasks / Activity | Estimated Time (hrs) | Actual Time (hrs) | Target Date of Completion | Actual Date Completion | Variance (hrs)
First Phase Familiarization with company,project,scope. | Obtaining and processing all the necessary information in regards that project for proposal. | 4 | 5 | 2023-08-04 | 2023-08-16 | -1 | At the beginning was little bit frustrated,that is why took longer.
| Signing of all necessary documents such as non-disclosure form, contract and agreements. | 2 | 2 | 2023-08-07 |  | 0 | The overcomplication of the procedure on the part of the industry has led to a large delay.
| Familiarization with a company,team meeting. | 5 | 5 | 2023-08-08 | 2023-08-08
The second phase WS2 field configurations complete and in version control | Search for the necessary information | 4 | 6 | 2023-08-20 |  | -2 | It is hard to work with a new tools,languages etc.
| Working on a model | 30 |  | 2023-08-31 |  | 30
| Model testing and version control | 5 |  | 2023-08-31 |  | 5
| Documentation | 1 |  | 2023-09-01 |  | 1
The third phase Script to run simulations through API complete and in version control. | Coding | 55 |  | 2023-09-20 |  | 55
| Model testing and version control | 20 |  | 2023-09-25 |  | 20
| Documentation | 1 |  | 2023-09-25 |  | 1
The fourth phase WS2 Observed data formatted and in version control. | Working with observed data, formating it. | 35 |  | 2023-10-04 |  | 35
| Model testing and version control | 8 |  | 2023-10-06 |  | 8
| Documentation | 1 |  | 2023-10-09 |  | 1
The fifth phase System for visualising model performance complete and in version control | Creating GUI | 65 |  | 2023-10-25 |  | 65
| Model testing and version control 80 | 9 |  | 2023-10-27 |  | 9
| Documentation | 1 |  | 2023-10-31 |  | 1
The sixth phase Integrate testing with Git hub pull request process | Integrate testing with Git hub pull request process | 50 |  | 2023-10-31 |  | 50
| Documentation | 4 |  | 2023-11-20 |  | 4
| Total time | 300 | 18 |  | Total Variance | 282